## Status Report
Futionality | Test Cases | Executed | Passed | Failed | Blocked / Pending | Descpoced | Comments / Risks | Tester(s) | Status | Results
Card Creation | 38 | 33 | 31 | 3 | 0 | 2 | Raise 3 defects for failed | KB MGAZI | Execution % Complete | 85%
Pin Management | 18 | 15 | 15 | 0 | 0 | 3 |  | KB MGAZI | Pass % | 90%
Data Management | 5 | 5 | 5 | 0 | 0 | 0 |  | KB MGAZI | Fail % | 10%
Authorization | 29 | 29 | 21 | 7 | 0 | 1 | raise 7 defects for failed | KB MGAZI | Blocked % | 0%
Card Status Change | 23 | 14 | 14 | 0 | 0 | 9 |  | KB MGAZI | Descoped % | 13%
| 113 | 96 | 86 | 10 | 0 | 15 |  | KB MGAZI | Start Date | 01/12/2025
[9 empty] | End Date (Planned) | 09/12/2025
[9 empty] | End Date (Actual) | 12/12/2025
Comments / Risks
Formula: =Executed/Total Test Cases*100
Formula: =Passed/Executed*100
Formula: =Failed/Executed*100
Formula: =Blocked/Executed*100

## CARD CREATION
Test Case ID | API / Feature | Title | Description | Pre-conditions | Steps | Test Data | Expected Result | Status
TC-CMS-001 | Client Management | Create client (valid) | Verify client creation with valid payload | API keys active | POST /createClient | Valid client payload | 201 Created + client_id | Pass
TC-CMS-002 | Client Management | Create client (missing fields) | Attempt client creation without required fields | API keys active | 1.POST /createClient 2. Verify Client is not successfully created due to missing fields | Missing mandatory fields | 400 Bad Request + error message | Pass
TC-CMS-003 | Client Management | Create client (duplicate) | Attempt client creation with existing client_id | Client exists | 1.POST /createClient 2. Verify Client is not successfully generated due to duplicate client, the client exist. | Duplicate client_id | 409 Conflict + error | Pass
TC-CMS-004 | Account Contract | Create account contract (valid) | Verify account contract creation | Client exists | 1.POST /createAccountContract 2. Verify account is successfully created with an existing Client ID. | Valid account payload | 201 Created + accountContractId | Pass
TC-CMS-005 | Account Contract | Create account contract (invalid client) | Attempt to create contract for non-existent client | Non-existent client | 1.POST /createAccountContract 2. Verify account is not successfully created with an invalid Client ID. | Invalid client_id | 404 Not Found + error | Pass
TC-CMS-006 | Account Contract | Invalid Product Code | Attempt account creation/update with a non-existent or invalidly formatted product_code. | Account contract exists | 1.POST /createAccountContract with product code ="XYZ123"(an invalid code). 2. Verify account is not successfully created | Invalid Product Code | 404 Not Found + error | Pass
TC-CMS-007 | Account Contract | Change account status (active → closed) | Change status of an active account | Account contract exists | POST /changeAccountContractStatus | Status=Closed | 200 OK + updated status | Pass
TC-CMS-008 | Account Contract | Non-Current Date | Attempt account creation/update using a date field (e.g., effective_date, start_date) that is set to a date other than today's calendar date (e.g., yesterday or tomorrow). | Account contract exists | 1. POST or PUT /createAccount with effective_date = 'YYYY-MM-DD' (where date is $\ne$ current date). 2. Verify account is not successfully created/updated. | Invalid/Non-current date | 404 Not Found + error | Pass
TC-CMS-009 | Account Contract | Change account status (invalid) | Attempt invalid status change | Account contract exists | POST /changeAccountContractStatus | Invalid status | 400 Bad Request | Pass
TC-CMS-010 | Card Contract | Create card contract (valid) | Create card linked to account contract | Account contract exists | 1.POST /createCardContract 2. Verify card is successfully created with valid card details and masked card number & EXID | Valid card payload | 201 Created + cardContractId | Pass
TC-CMS-011 | Card Contract | Create card contract (invalid account) | Attempt to create card for non-existent account | None | 1.POST /createCardContract 2. Verify card is successfully created with invalid account number | Invalid account | 404 Not Found | Pass
TC-CMS-012 | Card Contract | Attempt to Create Card Contract with Non-existent Product Code | Verify that the API rejects the request and returns an appropriate error when the provided product_code does not exist in the system's product catalog. | 1. A valid Account contract must exist in the system 2. A Product Code, such as that is not configured in the system must be identified for use in the payload. | 1.POST /createCardContract 2. Verify Card is not successfully created with invalid product code | Invalid Product Code | 400 | Pass
TC-CMS-013 | Card Contract | Attempt to Create Card Contract with Missing Emboss Name | Verify that the API rejects the request and returns an appropriate error when the mandatory emboss_name field is missing or excluded from the request payload. | 1. A valid Account contract must exist in the system 2. A valid product_code must be used to isolate the error to the missing emboss_name. | 1.POST /createCardContract 2. Verify Card is not successfully created without emboss name | Missing Embossing Name | 400 | Pass
TC-CMS-014 | Card Status Check | Successful Check (Active Card) | Verify the API correctly returns the status for an active card. | Card exists and its status is 'Active'. | 1. GET /card/check-status/0940042575292879.2. Verify response is 200 OK. 3. Verify the body contains status: "Active". | exid: "0940042575292879" | 200 OK + | Pass
TC-CMS-015 | Card Status Check | Successful Check (Lost Card) | Verify the API correctly returns the status for a card marked as lost. | Card exists and its status is 'Lost'. | 1. GET /card/check-status/1111222233334444 2. Verify response is 200 OK. 3. Verify the body contains status: "Lost". | exid: "1111222233334444" | 200 OK + | Pass
TC-CMS-016 | Card Status Check | Successful Check (Closed Card) | Verify the API correctly returns the status for a closed or cancelled card. | Card exists and its status is 'Closed'. | 1. GET /card/check-status/5555666677778888 2. Verify response is 200 OK. 3. Verify the body contains status: "Closed". | exid: "5555666677778888" | 200 OK + | Pass
TC-CMS-017 | Card Status Check | Non-existent ExID | Verify the system handles a request for a card ID that does not exist in the database. | None | 1. GET /card/check-status/0000000000000000 2. Verify response is 404 Not Found. | exid: "0000000000000000" | 404 Not Found + Error message | Pass
TC-CMS-018 | Card Status Check | Invalid ExID Format | Verify the system rejects an exid that is malformed (e.g., incorrect length, contains letters). | None | 1. GET /card/check-status/ABC1234. 2. Verify response is 400 Bad Request. | exid: "ABC1234" | 404 Not Found + Error message | Pass
TC-CMS-019 | Card Status Check | Empty ExID Parameter | Verify the system handles a request where the path parameter is empty. | None | 1. GET /card/check-status/. 2. Verify response is 404 Not Found (due to invalid route) or 400 Bad Request (if validation logic catches it). | exid: (empty string) | 404 Not Found + Error message | Pass
TC-CMS-020 | Card Activation | Successful Activation | Verify a card is successfully activated using a valid card ID (ExId), CVV, and future expiry date. | Card exists, is unactivated, and linked to client. | 1. POST /activateCard 2. Verify account status changes to 'Active'. | Valid EXID | 200 OK + Success message: "Card activated successfully." | Pass
TC-CMS-021 | Card Activation | Invalid ExId (Non-existent) | Verify the system rejects activation when the provided exId does not exist. | None | 1. POST /activateCard 2. Verify card is not activated. | Invalid/Non-existant EXID | 404 Not Found + Error message | Pass
TC-CMS-022 | Card Activation | Invalid CVV | Verify the system rejects activation when the provided cvv is incorrect for the card's exId. | Card exists and is unactivated. | 1. POST /activateCard 2. Verify card is not activated. | cvv: "999" (Incorrect/Invalid) | 400 Bad Request + Error message | Pass
TC-CMS-023 | Card Activation | Invalid Expiry Date (Past Date) | Verify the system rejects activation if the expiry date is in the past or formatted incorrectly (e.g., year before today). | Card exists and is unactivated. | 1. POST /activateCard 2. Verify card is not activated. | expiry: "01/24" (Past/Invalid) | 400 Bad Request + Error message | Pass
TC-CMS-024 | Card Reissue | Successful Card Reissue (Faulty Chip) | Verify a new copy is manufactured due to a malfunction, keeping all card details the same. | Card exists and is active. | 1. POST /reissueCard with reason_code: "CHIP". 2. Verify response is 200 OK. 3. Verify card details remain Same PAN, Same Expiry Date, Same CVV. | exId: "0940042575292879" reason_code: "CHIP" (Chip Malfunction) | 200 OK + Same PAN + Same Expiry Date + Same CVV | Fail
TC-CMS-025 | Card Reissue | Successful Card Renewal | Verify a card close to expiration is successfully renewed. | Card exists, is active, and is within the renewal window (e.g., 60 days before expiration). | 1. POST /reissueCard with reason_code: "REN". 2. Verify response is 200 OK. 3. Verify card details reflect New Expiry Date. | exId: "0940042575292879" reason_code: "REN" (Renewal) | 200 OK + Same PAN + New Expiry Date | Pass
TC-CMS-026 | Card Reissue | Successful Card Replacement (Stolen) | Verify a stolen card is successfully replaced, blocking the old card and issuing a new PAN. | Card exists and is active. | 1. POST /reissueCard with reason_code: "STO". 2. Verify response is 200 OK. 3. Verify card details reflect New PAN and New CVV. 4. Verify old card status is updated to 'Stolen'. | exId: "0940042575292879" reason_code: "STO" (Stolen) | 200 OK + New PAN + New Expiry Date + New CVV. | Pass
TC-CMS-027 | Card Reissue | Reissue Rejected (Invalid ExId) | Verify the system rejects the request when the provided exId does not exist. | None | 1. POST /reissueCard with non-existent exId. 2. Verify response is 404 Not Found. | exId: "0000000000000000" (Invalid/Non-existent) reason_code: "PRNT" (Printing Error) | 404 Not Found + Error message | Pass
TC-CMS-028 | Card Reissue | Invalid Reason Code | Verify the system rejects the request when an unsupported or unrecognized reason_code is provided. | Card exists and is active. | 1. POST /reissueCard with invalid reason_code. 2. Verify response is 400 Bad Request. | exId: "0940042575292879" reason_code: "UNKN" (Unknown code) | 400 Bad Request + Error message | Pass
TC-CMS-029 | Card Reissue | Replacement Rejected (Invalid Status) | Verify replacement is rejected if the card is already permanently closed or cancelled. | Card status is 'Cancelled'. | 1. POST /reissueCard with a closed card's exId. 2. Verify response is 400 Bad Request. | exId: "1234567890123456" reason_code: "DAM" (Damaged) | 400 Bad Request + Error | Fail
TC-CMS-030 | Card Reissue | Renewal Rejected (Not Due) | Verify renewal is rejected if the card's expiry date is far in the future (outside the renewal window). | Card expiry is $>6$ months away. | 1. POST /reissueCard with reason_code: "REN". 2. Verify response is 400 Bad Request. | exId: "0940042575292879" reason_code: "RENEW" | 400 Bad Request + Error | Fail
TC-CMS-031 | GET /cardContract | Get Card Contract (Valid) | Retrieve contract details for an existing card. | Card exists. | Execute GET request using the card's ID. | URL: /api/v1/cardContract/card_id | 200 OK + valid contract details returned. | Pass
TC-CMS-032 | GET /cardContract | Get Card Contract (Non-Existent) | Attempt to retrieve a contract that doesn't exist. | None. | Execute GET request using an invalid card ID. | URL: /api/v1/cardContract/invalid_id | 404 Not Found. | Pass
TC-CMS-033 | POST /verifyCardDetails | Verify Card Details (Valid) | Verify card information with a valid payload. | Card exists. | Execute POST request with valid authentication payload. | URL: /api/v1/verifyCardDetails Body: { "masked_pan": "...", "expiry": "..." } | 200 OK + Match confirmation. | Descoped
TC-CMS-034 | POST /verifyCardDetails | Verify Card Details (Invalid) | Attempt verification with wrong/mismatched card details. | Card exists. | Execute POST request with invalid verification payload. | URL: /api/v1/verifyCardDetails Body: { "masked_pan": "...", "expiry": "WRONG" } | 400 Bad Request or 403 Forbidden (Mismatch). | Descoped
TC-CMS-035 | GET /clientdetails | Retrieve Client ID (Valid) | Search and retrieve client ID using valid search criteria. | Client exists. | Execute POST request with valid search parameters (name, email). | URL: /api/v1/clients/searches | 200 OK + Client ID returned. | Pass
TC-CMS-036 | GET /clientdetails | Retrieve Client ID (Invalid) | Attempt to search for a non-existent client. | None. | Execute POST request with search parameters for a non-existent client. | URL: /api/v1/clients/searches | 404 Not Found or empty result list (200 OK with []). | Pass
TC-CMS-037 | GET/accountdetails | Retrieve Account Contract ID (Valid) | Search and retrieve account Contract ID using valid criteria. | Account exists. | Execute POST request with valid search parameters (e.g., client ID). | URL: /api/v1/accounts/searches | 200 OK + Account Contract ID returned. | Pass
TC-CMS-038 | GET/accountdetails | Retrieve Account Contract ID (Invalid) | Attempt search for non-existent account. | None. | Execute POST request with search parameters for a non-existent account. | URL: /api/v1/accounts/searches | 404 Not Found or empty result list. | Pass

## PIN MANAGEMENT
Test Case ID | API / Feature | Title | Description | Pre-conditions | Steps | Test Data | Expected Result | Status
TC-PM-001 | POST /set | Set a new PIN successfully | Validate setting the initial PIN using the /set endpoint. (Covers success path) | Card exists and active. PIN not set (pin_set='no'). | POST /set | Valid external_id & clear_pin. | 200 OK. pin_set updated to 'yes' and pvv created. | Pass
TC-PM-002 | POST /verify | Verify PIN (correct) | Verify the correct encrypted PIN block matches the stored PVV. (Covers success path) | Card exists, PIN set. | POST /verify | Correct encrypted current_pin_block. | 200 OK. success: true, message: "PIN verified.". | Pass
TC-PM-003 | POST /verify | Verify PIN (incorrect) | Decline verification if the entered PIN block is wrong. (Covers incorrect input) | Card exists, PIN set. | POST /verify | Wrong encrypted current_pin_block. | 401 Unauthorized. error: "Incorrect PIN.". | Pass
TC-PM-004 | POST /set | Decline: PIN already set (use /change) | Reject PIN setting if the pin_set flag is already 'yes'. (Covers /set logic) | Card exists, pin_set='yes'. | POST /set with valid data. | clear_pin: 1234 | 400 Bad Request. error: "PIN already set. Use /change instead.". | Pass
TC-PM-005 | POST /change | Decline: PIN not set (use /set) | Reject PIN change if the pin_set flag is 'no'. (Covers /change logic) | Card exists, pin_set='no'. | POST /change with valid data. | current_pin_block: Valid Block, new_clear_pin: 5678 | 400 Bad Request. error: "PIN not set. Use /set first.". | Pass
TC-PM-006 | POST /change | Change PIN (Valid) | verifies the successful execution of the PIN Change function (POST /change). The objective is to ensure that a user can update their PIN if they can successfully authenticate with the existing one. | Card exists, pin_set='yes', Card status='Active'. | POST /change with valid data. | Valid card_id, Correct current_pin_block, Valid new_clear_pin (4-12 digits) | 200 OK + PIN is updated in PVVstored), DB pin_attempts is reset to 0. | Pass
TC-PM-007 | POST /change | Decline: Incorrect current PIN block | Verify the PIN change is declined if the old PIN block is invalid. (Covers /change verification) | Card exists, PIN set. | Attempt to change PIN with incorrect current_pin_block. | current_pin_block: Incorrect Block, new_clear_pin: 5678 | 401 Unauthorized. error: "Incorrect current PIN.". | Pass
TC-PM-008 | POST /set | Decline: Invalid PIN Format (Too Long) | Verify PIN is rejected if it exceeds the maximum length (12 digits). (Covers isValidPin logic) | Card exists and active. | POST /set | clear_pin: "1234567890123" (13 digits) | 400 Bad Request. error: "Invalid PIN format (4-12 digits).". | Pass
TC-PM-009 | POST /change | HSM Error during Verification | Verify PIN Change fails gracefully with a 500 if the hsm.verifyPinBlock call fails. (Covers HSM error handling in /change) | Card exists and PIN set. HSM is mocked to throw a transient error during verification. | POST /change | current_pin_block: Valid Block, new_clear_pin: 5678 | 500 Internal Server Error. message: "HSM verification error...". PIN remains unchanged. | Descope
TC-PM-010 | POST /set | HSM Error during PVV Generation | Verify PIN Set fails gracefully with a $\text{500}$ if the hsm.generatePvv call fails. (Covers $\text{HSM}$ error handling in /set) | Card exists, PIN not set. $\text{HSM}$ is mocked to throw a transient error during PVV generation. | POST /set | clear_pin: 1234 | $\text{500 Internal Server Error}$. message: "Secure processing error: Could not encrypt PIN...". pin_set remains 'no'. | Descope
TC-PM-011 | POST /verify | Decline: Card Status Not Active | Verify PIN verification is disallowed if the card status is not Active. (Covers /verify status check) | Card exists. PIN set. Card status "Active" (e.g., "Blocked"). | POST /verify | current_pin_block: Valid Block | 400 Bad Request. error: "Card status is Blocked. Verification not allowed.". | Pass
TC-PM-012 | POST /change | Invalid Input: Missing Field | Verify 400 error if any required field (current_pin_block, new_clear_pin) is missing. (Covers /change input validation) | N/A | POST /change missing current_pin_block. | new_clear_pin: 5678 | 400 Bad Request. error: "Missing fields.". | Pass
TC-PM-013 | POST /set | Invalid Input: Missing Field | Verify 400 error if any required field (external_id, clear_pin) is missing. (Covers /set input validation) | N/A | POST /set missing clear_pin. | external_id: C-1001 | 400 Bad Request. error: "Missing mandatory fields.". | Pass
TC-PM-014 | POST /verify | Invalid Input: Missing Field | Verify 400 error if any required field (external_id, current_pin_block) is missing. (Covers /verify input validation) | N/A | POST /verify missing current_pin_block. | external_id: C-1001 | 400 Bad Request. error: "Missing mandatory fields.". | Pass
TC-PM-015 | POST /set | Decline: Card Not Found | Verify 404 error if the external_id does not exist. (Covers /set lookup) | Non-existent external_id. | POST /set | external_id: C-UNKNOWN-99, clear_pin: 1234 | 404 Not Found. error: "Card not found for EXID: C-UNKNOWN-99.". | Pass
TC-PM-016 | POST /change | Decline: Card Not Found | Verify 404 error if the external_id does not exist. (Covers /change lookup) | Non-existent external_id. | POST /change | external_id: C-UNKNOWN-99, current_pin_block: Block, new_clear_pin: 5678 | 404 Not Found. error: "Card not found.". | Pass
TC-PM-017 | POST /verify | Decline: Card Not Found | Verify 404 error if the external_id does not exist. (Covers /verify lookup) | Non-existent external_id. | POST /verify | external_id: C-UNKNOWN-99, current_pin_block: Block | 404 Not Found. error: "Card not found.". | Pass
TC-PM-018 | POST /set | DB Error during Update | Verify transaction rolls back/fails with $\text{500}$ if the $\text{DB}$ update fails. (Covers updatePin $\text{DB}$ error) | Card exists. $\text{DB}$ is mocked to fail the UPDATE query. | POST /set | external_id: C-1001, clear_pin: 1234 | $\text{500 Internal Server Error}$. message: "Database error during PIN update.". pin_set remains 'no'. | Descope

## DATA MANAGEMENT
Test Case ID | API / Feature | Title | Description | Pre-conditions | Steps | Test Data | Expected Result | Status
TC-DM-001 | Operation Management | Update client (valid) | Update client information successfully | Client exists | POST /updateClient | Valid client fields | 200 OK + updated client | Pass
TC-DM-002 | Operation Management | Update client (invalid) | Attempt to update non-existent client | None | POST /updateClient | Invalid client_id | 404 Not Found | Pass
TC-DM-003 | Operation Management | Update account contract (valid) | Update account contract fields | Account contract exists | POST /updateAccountContract | Valid contract fields | 200 OK + updated contract | Pass
TC-DM-004 | Operation Management | Update account contract (invalid) | Attempt to update non-existent account contract | None | POST /updateAccountContract | Invalid accountContractId | 404 Not Found | Pass
TC-DM-005 | Operation Management | Update card contract (valid) | Update card contract details | Card contract exists | POST /updateCardContract | Valid cardContract fields | 200 OK + updated card contract | Pass

## CARD STATUS CHANGE
Test Case ID | API/Feature | Title | Description | Pre-conditions | Steps | Test Data | Expected Result | Status
TC-CSC-001 | Card Status Update | P: Apply Temp Block (T) at Card Level | Verify T block works and affects only one card. | Account $\text{Active}$; Card X $\text{Active}$; Card Y $\text{Active}$. | Execute POST with block_code: "T" on Card X. | Body: { "external_id": "CardX", "block_code": "T" } | 1. API success (200). 2. Card X status becomes T (Blocked). 3. Card Y remains Active. | Pass
TC-CSC-003 | Card Status Update | P: Apply Perm Block (B) at Card Level | Validate B applies only to one card and is irreversible. | Account $\text{Active}$; Card X $\text{Active}$. | Execute POST with block_code: "B" on Card X. | Body: { "external_id": "CardX", "block_code": "B" } | 1. API success (200). 2. Card X status becomes B (Blocked). 3. Other cards remain Active. | Pass
TC-CSC-006 | Card Status Update | P: Apply Lost (L) at Card Level | Validate L applies correctly and triggers reissue. | Card X $\text{Active}$. | Execute POST with block_code: "L" on Card X. | Body: { "external_id": "CardX", "block_code": "L" } | 1. API success (200). 2. Card X status becomes L (Blocked). 3. System sets Reissue flag to True. | Pass
TC-CSC-007 | Card Status Update | P: Apply Stolen (S) at Card Level | Validate S applies correctly and flags PAN as compromised. | Card X $\text{Active}$. | Execute POST with block_code: "S" on Card X. | Body: { "external_id": "CardX", "block_code": "S" } | 1. API success (200). 2. Card X status becomes S (Blocked). 3. System flags PAN as compromised. | Pass
TC-CSC-009 | Card Status Update | P: Apply Fraud (F) at Card Level (Suspected) | Suspected fraud only impacts one card; assumed reversible. | Card X $\text{Active}$. | Execute POST with block_code: "F" on Card X. | Body: { "external_id": "CardX", "block_code": "F" } | 1. API success (200). 2. Card X status becomes F (Blocked). | Pass
TC-CSC-011 | Card Status Update | P: Apply Malfunction (M) at Card Level | Validate M applies only to the target card. | Card X $\text{Active}$. | Execute POST with block_code: "M" on Card X. | Body: { "external_id": "CardX", "block_code": "M" } | 1. API success (200). 2. Card X status becomes M (Blocked). | Pass
TC-CSC-014 | Card Status Update | P: Remove T Block Using _ | Valid reversal using the special removal code. | Card X status = T (Blocked). | Execute POST with block_code: "_" on Card X. | Body: { "external_id": "CardX", "block_code": "_" } | 1. API success (200). 2. Card X status reverts to Active. Message is "Temporary Block (T) successfully removed." | Pass
TC-CSC-015 | Card Status Update | P: Remove M Block Using _ | Valid reversal using the standard status code. | Card X status = M (Blocked). | Execute POST with block_code: "_" on Card X. | Body: { "external_id": "CardX", "block_code": "ACTIVE" } | 1. API success (200). 2. Card X status reverts to Active. | Pass
TC-CSC-016 | Card Status Update | P: Remove M Block Using _ | Valid reversal using the special removal code. | Card X status = M (Blocked). | Execute POST with block_code: "_" on Card X. | Body: { "external_id": "CardX", "block_code": "_" } | 1. API success (200). 2. Card X status reverts to Active. Message is "Malfunction Block (M) successfully removed." | Descope
TC-CSC-017 | Card Status Update | P: Remove Fraud Block (F) Using ACTIVE | Allowed removal for suspected fraud cases. | Card X status = F (Blocked) (Assumed reversible). | Execute POST with block_code: "ACTIVE" on Card X. | Body: { "external_id": "CardX", "block_code": "ACTIVE" } | 1. API success (200). 2. Card X status reverts to Active. | Descope
TC-CSC-018 | Card Status Update | N: Attempt Remove Fraud Block (F) Using _ | Not allowed, as _ only reverses T/M. | Card X status = F (Blocked). | Execute POST with block_code: "_" on Card X. | Body: { "external_id": "CardX", "block_code": "_" } | API returns 403 Forbidden. Error message specifies _ is only for T/M. Status remains F. | Pass
TC-CSC-019 | Card Status Update | N: Attempt Remove Fraud Block (F) Using ACTIVE (Irreversible) | Not allowed for confirmed fraud (irreversible). | Card X status = F (Blocked) (Assumed confirmed fraud). | Execute POST with block_code: "ACTIVE" on Card X. | Body: { "external_id": "CardX", "block_code": "ACTIVE" } | API returns 403 Forbidden. Error message indicates block is permanent/irreversible. Status remains F. | Descope
TC-CSC-020 | Card Status Update | N: Attempt Remove Fraud Block (F) Using _ (Irreversible) | Not allowed for confirmed fraud (irreversible). | Card X status = F (Blocked) (Assumed confirmed fraud). | Execute POST with block_code: "_" on Card X. | Body: { "external_id": "CardX", "block_code": "_" } | API returns 403 Forbidden. Error message indicates block is permanent/irreversible. Status remains F. | Descope
TC-CSC-021 | Card Status Update | N: Remove Permanent Block (B) Using ACTIVE | Invalid reversal attempt on permanent block. | Card X status = B (Blocked). | Execute POST with block_code: "ACTIVE" on Card X. | Body: { "external_id": "CardX", "block_code": "ACTIVE" } | API returns 403 Forbidden. Error message indicates block is permanent. Status remains B. | Descope
TC-CSC-022 | Card Status Update | N: Remove Permanent Block (B) Using _ | Not allowed, as _ only reverses T/M. | Card X status = B (Blocked). | Execute POST with block_code: "_" on Card X. | Body: { "external_id": "CardX", "block_code": "_" } | API returns 403 Forbidden. Error message specifies _ is only for T/M. Status remains B. | Pass
TC-CSC-023 | Card Status Update | N: Remove Lost (L) Using ACTIVE | Not allowed, as L requires reissue. | Card X status = L (Blocked). | Execute POST with block_code: "ACTIVE" on Card X. | Body: { "external_id": "CardX", "block_code": "ACTIVE" } | API returns 403 Forbidden. Error message indicates block is permanent/requires reissue. Status remains L. | Descope
TC-CSC-024 | Card Status Update | N: Remove Lost (L) Using _ | Not allowed, as _ only reverses T/M. | Card X status = L (Blocked). | Execute POST with block_code: "_" on Card X. | Body: { "external_id": "CardX", "block_code": "_" } | API returns 403 Forbidden. Error message specifies _ is only for T/M. Status remains L. | Pass
TC-CSC-025 | Card Status Update | N: Remove Stolen (S) Using ACTIVE | Not allowed, as S requires reissue and PAN compromise handling. | Card X status = S (Blocked). | Execute POST with block_code: "ACTIVE" on Card X. | Body: { "external_id": "CardX", "block_code": "ACTIVE" } | API returns 403 Forbidden. Error message indicates block is permanent/requires reissue. Status remains S. | Descope
TC-CSC-026 | Card Status Update | N: Remove Stolen (S) Using _ | Not allowed, as _ only reverses T/M. | Card X status = S (Blocked). | Execute POST with block_code: "_" on Card X. | Body: { "external_id": "CardX", "block_code": "_" } | API returns 403 Forbidden. Error message specifies _ is only for T/M. Status remains S. | Pass
TC-CSC-027 | Card Status Update | N: Remove Damaged (D) Using ACTIVE | Not allowed, as D requires reissue. | Card X status = D (Blocked). | Execute POST with block_code: "ACTIVE" on Card X. | Body: { "external_id": "CardX", "block_code": "ACTIVE" } | API returns 403 Forbidden. Error message indicates block is permanent/requires reissue. Status remains D. | Descope
TC-CSC-028 | Card Status Update | N: Remove Damaged (D) Using _ | Not allowed, as _ only reverses T/M. | Card X status = D (Blocked). | Execute POST with block_code: "_" on Card X. | Body: { "external_id": "CardX", "block_code": "_" } | API returns 403 Forbidden. Error message specifies _ is only for T/M. Status remains D. | Pass
TC-CSC-029 | Card Status Update | N: Remove Closed (C) Using ACTIVE | Not allowed, as C is a final termination status. | Card X status = C (Inactive/Closed). | Execute POST with block_code: "ACTIVE" on Card X. | Body: { "external_id": "CardX", "block_code": "ACTIVE" } | API returns 403 Forbidden. Error message indicates block is permanent/final. Status remains C. | Descope
TC-CSC-030 | Card Status Update | N: Remove Closed (C) Using _ | Not allowed, as _ only reverses T/M. | Card X status = C (Inactive/Closed). | Execute POST with block_code: "_" on Card X. | Body: { "external_id": "CardX", "block_code": "_" } | API returns 403 Forbidden. Error message specifies _ is only for T/M. Status remains C. | Pass

## AUTHORIZATION
Test Case ID | API/Feature | Title | Description | Pre-conditions | Steps | Test Data | Expected Result | Status
AUTH-001 | /depositFunds | Successful Deposit (Standard) | Verify funds are correctly added to an Active account, increasing the balance. | Account is Active. | 1. Send POST request to /depositFunds. | account_number: ACC-2001, amount: "500.00", currency_code: "ZAR" | HTTP 200. success: true, new_balance: Initial Balance + 500.00. | Pass
AUTH-002 | /depositFunds | Deposit Declined - Account Frozen | Verify deposit is rejected if the account is in a Frozen status. | Account status = Frozen. | 1. Send POST request. | account_number: ACC-2002, amount: "100.00", currency_code: "ZAR" | HTTP 403. success: false, error: "Account is Frozen and cannot receive funds.". Balance unchanged. | Pass
AUTH-003 | /depositFunds | Deposit Declined - Account Not Found | Verify deposit is rejected if the account number does not exist in the database. | Use a non-existent account_number. | 1. Send POST request. | account_number: ACC-NON-EXIST, amount: "10.00", currency_code: "ZAR" | HTTP 403. success: false, error: "Account not found.". | Pass
AUTH-004 | /depositFunds | Deposit Declined - Wrong Currency | Verify deposit is rejected if the provided currency_code does not match the BASE_CURRENCY (ZAR). | BASE_CURRENCY is ZAR. | 1. Send POST request with USD. | account_number: ACC-2004, amount: "200.00", currency_code: "USD" | HTTP 500. success: false, error: "Deposit currency must match base currency...". Balance unchanged. | Pass
AUTH-005 | /depositFunds | Boundary Check - Minimum Deposit Amount | Verify the system accepts the smallest possible positive amount (e.g.,0.01 | Account is Active. | 1. Send POST request with amount "0.01". | account_number: ACC-2005, amount: "0.01", currency_code: "ZAR" | HTTP 200. success: true, new_balance: Initial Balance + 0.01. | Pass
AUTH-006 | /depositFunds | Boundary Check - Large Deposit Amount | Verify the system handles a high-value deposit without error (assumes BIGINT or high precision decimal support). | Account is Active. | 1. Send POST request with a large amount. | account_number: ACC-2006, amount: "999999.00", currency_code: "ZAR" | HTTP 200. success: true, new_balance: Correctly calculated high balance. | Pass
AUTH-007 | /depositFunds | Invalid Input - Missing account_number | Verify 400error for missing mandatory field. | N/A | 1. Send POST request missing account_number. | account_number: null, amount: "100.00", currency_code: "ZAR" | HTTP 400. success: false, error: "Missing mandatory fields.". | Pass
AUTH-008 | /depositFunds | Invalid Input - Zero/Negative Amount | Verify 400 error for non-positive deposit amount. | N/A | 1. Send POST request with amount "0.00". | account_number: ACC-2008, amount: "0.00", currency_code: "ZAR" | HTTP 400 success: false, error: "Missing mandatory fields.". | Pass
AUTH-009 | /depositFunds | Invalid Input - Non-Numeric Amount | Verify 400 error for non-numeric data in amount field. | N/A | 1. Send POST request with amount: "Fifty". | account_number: ACC-2009, amount: "Fifty", currency_code: "ZAR" | HTTP 400}. success: false, error: "Missing mandatory fields.". | Pass
AUTH-010 | /depositFunds | Unauthenticated Access Check | Verify that the Bearer token authentication middleware (authenticateBearer) is correctly applied and rejects requests without a valid token. | No Bearer Token provided or an Invalid Token provided. | 1. Send POST} request without the Authorization header. | account_number: ACC-2010, amount: "100.00", currency_code: "ZAR" | HTTP 401 response: "Unauthorized". | Pass
AUTH-011 | /authorize | POS Purchase – Approved | Validate POS transaction at in store machine. | Active debit card, sufficient balance | Send POS purchase request | Amount=R100, MerchantID=M-001 | Response=Approved, Fee=R0 | Pass
AUTH-012 | /authorize | POS Purchase – Insufficient Funds | Decline POS transaction if insufficient balance. | Active debit card, low balance | Send POS purchase request | Amount=R500 | Response=Declined, Reason=InsufficientFunds | Pass
AUTH-013 | /authorize | Online Payment – Approved | Validate online eCommerce transaction. | Active debit card, sufficient balance | Send online payment request | Amount=R300, MerchantID=ECOMM-01 | Response=Approved, Fee=R0 | Pass
AUTH-014 | /authorize | Online Payment – Exceed Limit | Decline online transaction if exceeds daily limit | Active debit card, daily limit=R2000 | Send online payment request | Amount=R2500 | Response=Declined, Reason=ExceedsLimit | Pass
AUTH-015 | /authorize | Scan-to-Pay / QR – Approved | Validate QR payment via mobile app | Active debit card, sufficient balance | Send QR payment request | Amount=R100, MerchantID=QR-123 | Response=Approved, Fee=R0 | FAIL
AUTH-016 | /authorize | Scan-to-Pay / QR – Frozen Card | Decline QR payment if card frozen | Card status=Frozen | Send QR payment request | Amount=R100 | Response=Declined, Reason=Card Frozen | FAIL
AUTH-017 | /authorize | Mobile Wallet Payment – Approved | Validate Apple/Google/Samsung Pay transaction | Active debit card, sufficient balance | Send mobile wallet request | Amount=R200 | Response=Approved, Fee=R0 | FAIL
AUTH-018 | /authorize | Mobile Wallet Payment – Invalid Token | Decline transaction with invalid wallet token | Active debit card | Send mobile wallet request | Token=Invalid | Response=Declined, Reason=Invalid Token | FAIL
AUTH-019 | /authorize | ATM Cash Withdrawal – Approved | Validate domestic ATM withdrawal | Active debit card, sufficient balance | Send ATM withdrawal request | Amount=R1000, ATMID=ATM01 | Response=Approved, Fee=R0 | Pass
AUTH-020 | /authorize | ATM Withdrawal – Insufficient Funds | Decline ATM withdrawal if balance < amount | Active debit card, low balance | Send ATM withdrawal request | Amount=R1500 | Response=Declined, Reason=Insufficient Funds | Pass
AUTH-021 | /authorize | International ATM Withdrawal – Approved | Validate withdrawal at international ATM enabled | Active debit card, sufficient balance, international enabled | Send ATM withdrawal request | Amount=R1000, TxnCode=INT-1 | Response=Approved, Fee=calculated | Pass
AUTH-022 | /authorize | International ATM Withdrawal – Card Expired | Decline transaction if card expired | Card status=Expired | Send international withdrawal request | Amount=R500 | Response=Declined, Reason=Expired | FAIL
AUTH-023 | /authorize | ATM Balance Inquiry – Success | Validate balance inquiry | Active debit card | Send balance inquiry request | ATMID=ATM01 | Response=Approved, Balance=available | Pass
AUTH-024 | /authorize | ATM Balance Inquiry – Frozen Card | Decline inquiry if card frozen | Card status=Frozen | Send balance inquiry request | ATMID=ATM01 | Response=Declined, Reason=Card Frozen | FAIL
AUTH-025 | /authorize | Electricity Payment – Approved | Validate electricity payment via app/online | Active debit card, sufficient balance | Send bill payment request | Amount=R100, BillType=Electricity | Response=Approved, Fee=R1 | Pass
AUTH-026 | /authorize | Electricity Payment – Insufficient Funds | Decline payment if balance < amount | Active debit card, low balance | Send bill payment request | Amount=R200 | Response=Declined, Reason=Insufficient Funds | Pass
AUTH-027 | /authorize | Vouchers / Lotto Payment – Approved | Validate digital voucher/lotto payment | Active debit card, sufficient balance | Send voucher payment request | Amount=R50 | Response=Approved, Fee=R0 | Pass
AUTH-028 | /authorize | Vouchers / Lotto – Frozen Card | Decline if card frozen | Card status=Frozen | Send voucher payment request | Amount=R50 | Response=Declined, Reason=Card Frozen | FAIL
AUTH-029 | /authorize | Capitec Pay – Approved | Validate digital payments via Capitec Pay | Active debit card | Send Capitec Pay request | Amount=R75 | Response=Approved, Fee=R1 | Descope